## Slide 1: 37E01500 Project Management and Consulting Practice Project Quality and Risk management
Matti Rossi, professor, Jari Ruokolainen, Adjunct professor
Dept. of Information and Service Economy
Lecture 5, March 3, 2017

## Slide 2: Learning objectives
Be able to list several planning tasks and outputs for project quality and risk management
Discuss the project quality and risk management tasks, and explain the purpose and contents of a quality and risk management plan, quality metrics, quality checklists and risk-related contractual agreements in risk management planning
Explain tasks in project closing

## Slide 3: Contents
Risk management and quality
Communications planning
This lecture refers to the course book
  Schwalbe (2013) Revised An Introduction to Project Management, Ch. 4
Initiating
Planning
Executing
Monitoring/ Controlling
Closing

## Slide 4: Thoughts to be considered: based on experience
Plans versus needs
Ultimately the need can be something else than planned
We plan something that we do finally need
What are the customers’ latent needs?
Relationship building How I have manage

## Slide 5: How have I managed the project quality?
I ensure that the right project structure is in place
  Project hierarchy
  Project plans are done and updated
  Having meeting both formal and informal meetings
I ensure that the decision making is open
  Can be tracked
  Meeting minutes are done
  Project budget is discussed
  Decision and meetings are discussed prior to the meeting
  Comparisons to the goals
  No surprises

## Slide 6: How have I managed the project quality?
The quality of the main deliverables
  Tested enough well and many times
  As I do research in management sciences, many of project outcomes have ended to the publication
My pitfalls
  To be inpatients – expecting results sooner than later
    the baby to born symptom
  Not discuss problems right way in the past
  Managing expectations – too high
    Selling and marketing phenomenon

## Slide 7: My rule of thumbs
Satisfaction of the stakeholders depends on your capability to build relationships
Simplify, simplify and simplify
  Comment from the boss – everyone could have done it
Adjust the project based on the skills of the people if can not be done than change the people
From the portfolio management point of view:
  If no costs are shown in first months, there will be no projects
Risks are listed
  If the project fails, is the reason in the risk list?

## Slide 8: About project success
A project is successful when
  all relevant stakeholders are satisfied with the results
  project goals are met (time, scope, cost, quality)
Process vs. end result success
  it is not always clear, whether the project is successful or not (e.g. project with long-term impact, multi-party projects, large scale information systems projects ERP etc.)

## Slide 9: Why some projects fail?
Some common pitfalls
  No consensus on goals, failed mutual understanding, poor commitment
  Lack of user/customer involvement
  Unrealistic time scales
  Poor requirements
  Scope creep
  No change control system
  Poor feedback

## Slide 10: Some failures
Smaller scope
Delayed schedule
Time
Cost
Scope
Time
Cost
Scope

## Slide 11: Some failures (cont.)
Costs out of control
Pancake
Time
Cost
Scope
Time
Cost
Scope

## Slide 12: Planning processes and outputs for project quality, HR and risk mgmt
Knowledge area | Planning process | Outputs
Project quality management | Plan quality | Quality management plan Quality metrics & checklists Process improvement plan Project document updates
Project HR management | Human resource plan | Human resource management plan
Project communications management | Plan communications | Communications management plan Project document updates
Project risk management | Plan risk management Identify risks Perform risk analyses Plan risk responses | Risk management plan Risk register & updates Risk-related contract decisions Project document updates
Project procurement management | Plan procurements | Procurement management plan Procurement statement of work Make-or-buy decisions Procurement documents Source selection criteria Change requests

## Slide 13: Project quality management planning tasks
Project quality management ensures that the project will satisfy the stated or implied needs for which it was undertaken
Key outputs produced as part of project quality management include a quality management plan, project dashboard, quality metrics descriptions, and quality checklists

## Slide 14: What is quality?
The International Organization for Standardization (ISO) defines quality as “the degree to which a set of inherent characteristics fulfill requirements” (ISO9000:2000)
Other experts define quality based on conformance to requirements and fitness for use.
  Conformance to requirements means that the project’s processes and products meet written/agreed specifications
  Fitness for use means that a product can be used as it was intended
The customer ultimately decides that the quality level is acceptable

## Slide 15: Quality planning and quality management plan
Quality planning includes identifying which quality standards are relevant to the project and how best to satisfy those standards
It also involves designing quality into the products of the project as well as the processes involved in managing the project
Like other plans, the size and complexity of quality management plans varies to meet project needs

## Slide 16: Sample quality management plan
Project Name: Just-In-Time Training Project
Introduction: The main goal of this project is to develop a new training program that provides just-in-time training to employees on key topics, including supplier management, negotiating skills, project management, and software applications.
Quality Standards: The standards that apply to this project are:
Survey standards: Following corporate standards for developing and administering surveys to employees. Quantitative and qualitative information will be collected. Quantitative data will use a 5-point Likert scale. A corporate expert on surveys will review the survey before it is administered.
Supplier selection standards: See Attachment 2 for corporate standards regarding supplier selection. Past performance and developing partnerships will be key issues for this project.
Training standards: See Attachment 3 for corporate standards regarding training. The training provided as part of this project will be available in several formats, including instructor-led, CD/ROM, and web-based. Employees will have access to CD/ROM and web-based training at any time to meet individual and business needs on a just-in-time manner.

## Slide 17: Sample quality management plan (cont.)
Quality performance metrics. Several metrics apply to this project, including:
Survey response rate: For the survey to be successful, a response rate of at least 30% must be achieved.
Course evaluations: All course participants must complete a course evaluation in order for their training to be tracked in our corporate professional development system. In addition to evaluations on more detailed topics, there will be an overall course rating. The average course rating should be at 3.0 or better on a 5.0 scale.
Problem Reporting and Corrective Action Processes: Project plans will include clear roles and responsibilities for all stakeholders. The person responsible for an individual task should report problems to appropriate managers and work with them to determine and implement corrective actions. Major problems should be brought to the attention of the project manager, who should elevate problems that might affect project success, including meeting scope, time, cost, and quality goals, to the project steering committee and then the project sponsor. It is crucial to address problems as early as possible and develop several alternative solutions.
Supplier Quality and Control: The project manager will closely monitor work performed by suppliers, with assistance from our supplier management department. All contracts must clearly state quality standards, metrics, etc.

## Slide 18: Quality metrics
A metric is a standard of measurement
Metrics allow organizations to measure their performance in certain areas and to compare them over time or with other organizations
Examples of common metrics used by organizations include failure rates of products produced, availability of goods and services, and customer satisfaction ratings

## Slide 19: Sample quality metrics
The Just-In-Time Training project’s success criteria, as documented in the scope statement, included metrics based on:
  Time: Completing the project within one year
  Customer satisfaction: Achieving an average course evaluation of at least 3.0 on a 5.0 scale
  Cost reduction: Recouping the cost of the project in reduced training costs within two years after project completion
Many organizations use charts to keep track of metrics, such as a project dashboard—a graphical screen summarizing key project metrics

## Slide 20: A sample project dashboard

## Slide 21: Quality checklists
A checklist is a list of items to be noted or consulted
It helps project teams verify that a set of required topics or steps has been covered or performed
A single project can have many different checklists, such as for:
  Interviewing project team members
  Selecting suppliers
  Reviewing important documents
  Ensuring a room is ready for training

## Slide 22: Sample quality metrics description
Project Name: Just-In-Time Training Project
The following quality metrics apply to this project:
Survey response rate: In order for the survey to be successful, a response rate of at least 30% must be achieved. Most surveys will be administered online using the standard corporate survey software, which can track the response rate automatically. If the response rate is less than 30% one week after the survey is sent out, the project manager will alert the project steering committee to determine corrective action.
Course evaluations: All course participants must complete a course evaluation so that their training can be tracked in our corporate professional development system. In addition to evaluations on more detailed topics, there will be an overall course rating. The average course rating should be at least 3.0, with 5 being the highest score. For example, a question might be as follows: “My overall evaluation of this course is ……” Respondents would select 1 for Poor, 2 for Fair, 3 for Average, 4 for Good, or 5 for Excellent.

## Slide 23: To be discussed
What would be your quality metrics in your on-going project?

## Slide 24: Project Human Resource management planning tasks
“People are our most important asset.” People determine the success and failure of organizations and projects.
Project human resource management is concerned with making effective use of the people involved with a project
The main output produced as part of project human resource management planning is a project human resource management plan, which includes a project organizational chart, a responsibility assignment matrix, a resource histogram, and a staffing management plan
Other topics, such as motivation and dealing with people problems, are discussed in Chapter 6 in the course handbook.

## Slide 25: Project organizational charts
Similar to a company’s organizational chart, a project organizational chart is a graphical representation of how authority and responsibility is distributed within the project
The size and complexity of the project determines how simple or complex the organizational chart is

## Slide 26: A sample project organizational chart

## Slide 27: Responsibility assignment matrices
A responsibility assignment matrix (RAM) is a matrix that maps the work of the project as described in the work breakdown structure (WBS) to the people responsible for performing the work
For smaller projects, it is best to assign WBS activities to individuals; for larger projects, it is more effective to assign the work to organizational units or teams
RACI charts are a type of RAM that show Responsibility (who does the task), Accountability (who signs off on the task or has authority for it), Consultation (who has information necessary to complete the task), and Informed (who needs to be notified of task status/results) roles for project stakeholders

## Slide 28: A sample RACI chart
Tasks | Kristin | Jamie | Mohamed | Supplier A
Needs assessment | A | R | C | I
Research of existing training | I | R, A | C | I
Partnerships | R, A | I | I | C
Course development | A | C | C | R
Course administration | I | A | R | I
Course evaluation | I | A | R | I
Stakeholder communications | R, A | C | C | C
R: Responsible A: Accountable C: Consulted I: Informed

## Slide 29: Project web sites
Project Web sites provide a centralized way of delivering project documents and other communications
Some project teams also create blogs—easy-to-use journals on the Web that allow users to write entries, create links, and upload pictures, while allowing readers to post comments to particular journal entries
Project teams can develop project Web sites using Web-authoring tools, such as SharePoint Designer or Macromedia Dreamweaver; enterprise project management software, if available; or a combination of the two approaches
Part of the Web site might be open to outside users, whereas other parts might be accessible only by certain stakeholders
It is important to decide if and how to use a project Web site to help meet project communications requirements

## Slide 30: Project risk management planning tasks
PMI defines a project risk as an uncertainty that can have a negative or positive effect on meeting project objectives
Note that some people only view risks as negative and call positive risks opportunities
Key outputs include a risk management plan, a probability/impact matrix, a risk register, and risk-related contractual agreements

## Slide 31: Social acceptability of risk
The acceptability of a risk is determined by human, social and political considerations.
In most societies, the boundaries between the regions are pushed upwards with time i.e. society is less willing to accept risk
  For example, the costs of cleaning up pollution may be less than the costs of preventing it but this may not be socially acceptable.
Risk assessment is subjective
  Risks are identified as probable, unlikely, etc. This depends on who is making the assessment.

## Slide 32: Some potential areas of risks

## Slide 33: Risk assessment
Estimate the risk probability and the risk severity.
It is not normally possible to do this precisely so relative values are used such as ‘unlikely’, ‘rare’, ‘very high’, etc.
The aim must be to exclude risks that are likely to arise or that have high severity.

## Slide 34: Risk management plans
A risk management plan documents the procedures for managing risk throughout the life of a project
The general topics that a risk management plan should address include the methodology for risk management, roles and responsibilities, budget and schedule estimates for risk-related activities, risk categories, probability and impact matrices, and risk documentation

## Slide 35: Other risk plans
Contingency plans are predefined actions that the project team will take if an identified risk event occurs
Fallback plans are developed for risks that have a high impact on meeting project objectives, and are put into effect if attempts to reduce the risk are not effective; sometimes called contingency plans of last resort
Contingency reserves or contingency allowances are funds held by the project sponsor that can be used to mitigate cost or schedule overruns if unknown risks occur

## Slide 36: Risk events and probability/impact matrices
Risk events refer to specific, uncertain events that may occur to the detriment or enhancement of the project
  Negative risk events include the performance failure of a product produced as part of a project, delays in completing work as scheduled, increases in estimated costs, supply shortages, litigation against the company, and strikes
  Positive risk events include completing work sooner than planned or at an unexpectedly reduced cost, collaborating with suppliers to produce better products, and obtaining good publicity from the project
  You can chart the probability and impact of risk events on a matrix

## Slide 37: A sample risk probability / impact matrix
Source: Schwalbe, Information Technology Project Management, Sixth Edition, 2010

## Slide 38: Risk-related contractual agreements
Work done by outside suppliers or sellers should be well documented in contracts, which are mutually binding agreements that obligate the seller to provide the specified products or services, and obligate the buyer to pay for them
Project managers should include clauses in contracts to help manage project risks by using:
  Incentive or penalty clauses
  Certain types of contracts, such as fixed-price contracts, to reduce their risk of incurring higher costs than expected
  Competition for supplying goods and services to help reduce negative risks and enhance positive risks on projects

## Slide 39: The topic to be discussed
What are the risks in your projects ? And how are you planned to mitigate them?

## Slide 40: Questions
Questions ?