## Backlog
Task | Points | Owner | Status
Connect pc to pump, create program to control it from pc | 1
Create a 4G/5G connection with the modem | 2
Set up a server to make use of 4G/5G connection, and to be able to send commands to the pump | 4
Create a client that is able to send a continuous signal to the pump to keep it running | 3
Connect client to server, that is continuously monitoring for a signal to turn on pump | 3
Design USB interfacing with the client PC | 2 |  | Planning
Design control program to turn pump on/off | 1 |  | Planning
Connect pump control to modem allowing info to be sent to and from the pump (using NUC) | 1 |  | Planning
Establish 4g/5g communication between pump modem and server PC | 3 |  | Planning
create mobile server to monitor and control pump | 4 |  | Planning
establish connection between server and client | 4 |  | Planning
add actions for edge cases (eg. connection lost) | 2 |  | Planning
(opt?) add security bewteen client and server | 1 |  | Planning
Set up the devices. | 2
Examine the networking documentation and provide summary | 4
Examine pump control methods | 1
Establish a test connection. | 2
Test the pump controls. | 1
Draw a UML diagram of the whole system. | 2
Draw a UML diagram of each individual part. | 5
Design a code structure based on the features to implement. | 3
Set up the code classes and functions. | 2
Feature #1 | 3
Feature #2 | 3
Feature #3 | 3
Feature #4 | 3
Feature #5 | 3
Test the functions and methods (Sprint 1) | 4
Debug the found problems / refactor (Sprint 1) | 6
Test the functions and methods (Sprint 2) | 2
Debug the found problems / refactor (Sprint 2) | 3
Test the functions and methods (Sprint 3) | 2
Debug the found problems / refactor (Sprint 3) | 3

## Sprint1
3-7.05 | Task | Points | Owner | Status

## Sprint2
10-14.5 | Task | Points | Owner | Status

## Sprint3
17-21.05 | Task | Points | Owner | Status

## Sprint4
24-28.05 | Task | Points | Owner | Status