## Sheet3
Skanska - Juslenia case
Interior phase scheduling |  |  | Note: T= Toimisto = Office
Target Schedule for interior work: |  |  | Note: L = Laboratory
| Areas |  | Basement floor | [5 empty] | 1st floor | [7 empty] | 2nd floor | [7 empty] | 3rd Floor | [8 empty] | 4th floor | [7 empty] | 5th floor | [6 empty] | 6th Floor
| Floor | Consumption Rate (man hours per unit) | 0T1 | 0T2 | 0T3 | 0T4 | 0T5 | 0T6 | 1T1 | 1T2 | 1T3 | 1T4 | 1L1 | 1L2 | 1L4 | 1L5 | 2T1 | 2T2 | 2T3 | 2T4 | 2L1 | 2L2 | 2L4 | 2L5 | 3T1 | 3T2 | 3T3 | 3T4 | 3L1 | 3L2 | 3L3 | 3L4 | 3L5 | 4T1 | 4T2 | 4T3 | 4T4 | 4L1 | 4L2 | 4L3 | 4L4 | 5T2 | 5T3 | 5T4 | 5L1 | 5L2 | 5L3 | 5L4 | 6T2 | 6T3 | 6L1 | 6L2 | Units | Optimal Crew Size | Subcontractor
Item
1 | Dust binder painting | 1 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | mh | 2 | Dust binder painting
2 | Plasterwork 1 (for wet areas) | 0.09 | 448 | 0 | 0 | 26.32 | 0 | 410.28 | 67.64 | 648.62 | 606.9 | 194.66 | 577.7 | 907.68 | 1138.12 | 120.32 | 275.26 | 340.24 | 248.2 | 10 | 527.56 | 976.04 | 484.96 | 194.56 | 275.34 | 281.26 | 274.28 | 10 | 552.2 | 937.74 | 574.16 | 819.88 | 120 | 260.04 | 280.58 | 276.02 | 10 | 130.48 | 1021.1 | 506.34 | 638.04 | 280.12 | 284.82 |  | 79.58 | 895.36 | 619.78 | 504.72 | 325.5 | 870.92 | 897.9 | 364.28 | m2 | 2 | Plasterwork
3 | Common hanger system | 1 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | mh | 2
4 | Drywall frame and 1st side | 0.4 | 125 | 63 | 158 |  |  | 97 | 112 | 63 | 121 | 127 | 58 | 450 | 212 | 78 | 346 | 445 | 493 | 404 | 152 | 255 | 116 | 85 | 131 | 192 | 194 | 56 | 69 | 184 | 100 | 149 | 3 | 163 | 197 | 187 | 64 | 99 | 142 | 141 | 51 | 282 | 164 | 37 | 114 | 151 | 330 | 64 | 231 |  |  | 44 | m2 | 2 | Drywall
5 | In-Wall electrical | 1 | 24 | 30 | 19 | 51 | 9 | 29 | 123 | 60 | 58 | 43 | 50 | 113 | 65 | 36 | 52 | 98 | 34 | 98 | 129 | 239 | 48 | 40 | 63 | 57 | 55 | 75 | 176 | 134.4 | 101.2 | 94 | 26.4 | 56.4 | 55.2 | 51.6 | 40.4 | 192.8 | 0 | 138 | 72 | 74 | 89.6 | 30.4 | 277.6 | 127.6 | 82.4 | 0 |  |  |  |  | mh | 1 | Electrical
6 | Drywall insulation and 2nd side | 0.15 | 125 | 63 | 158 |  |  | 97 | 112 | 63 | 121 | 127 | 58 | 450 | 212 | 78 | 346 | 445 | 493 | 404 | 152 | 255 | 116 | 85 | 131 | 192 | 194 | 56 | 69 | 184 | 100 | 149 | 3 | 163 | 197 | 187 | 64 | 99 | 142 | 141 | 51 | 282 | 164 | 37 | 114 | 151 | 330 | 64 | 231 |  |  | 44 | m2 | 2 | Drywall
7 | Electric channels (Sähkökouru) | 1 | 4 | 10 | 0 | 35 | 0 | 6 | 50 | 22 | 34 | 6 | 22 | 46 | 4 | 20 | 10 | 10 | 0 | 0 | 85 | 140 | 24 | 16 | 16 | 10 | 0 | 6 | 105 | 110 | 65 | 58 | 16 | 0 | 6 | 0 | 8 | 0 | 0 | 0 | 46 | 4 | 0 | 0 | 500 | 72 | 38 | 0 |  |  |  |  | mh | 1 | Electrical
8 | Sprinkler Rough | 1 | 190.0966 | 74.5443 | 47.7497 | 47.0728 | 0 | 91.7648 | 116.389 | 223.712 | 98.4543 | 0 | 0 | 0 | 0 | 35.8071 | 94.6442 | 136.316 | 107.2012 | 138.311 | 0 | 0 | 0 | 40.0009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216.125 | 0 | mh | 1 | Fire Sprinkler
9 | Plasterwork 2 (Drywall, ceiling) | 0.08 | 1743 | 567 | 496 | 328.32 | 565 | 1429.3 | 704 | 967 | 1066 | 616 | 888 | 2044 | 1834 | 286 | 1013 | 891 | 836 | 414 | 1110 | 1536 | 892 | 365 | 1013 | 891 | 836 | 414 | 1006 | 1308 | 800 | 470 | 111 | 1013 | 891 | 836 | 414 | 1193 | 1306 | 788 | 921 | 1207 | 725 | 170 | 491 | 1266 | 1380 | 786 | 787.74 | 950.82 | 898 | 611.28 | m2 |  | Plasterwork
10 | Painting - first coat | 0.04 | 1743 | 567 | 496 | 328.32 | 565 | 1429.3 | 704 | 967 | 1066 | 616 | 888 | 2044 | 1834 | 286 | 1013 | 891 | 836 | 414 | 1110 | 1536 | 892 | 365 | 1013 | 891 | 836 | 414 | 1006 | 1308 | 800 | 470 | 111 | 1013 | 891 | 836 | 414 | 1193 | 1306 | 788 | 921 | 1207 | 725 | 170 | 491 | 1266 | 1380 | 786 | 787.74 | 950.82 | 898 | 611.28 | m2 |  | Painting
11 | Acoustic insulation | 0.12 |  | 316 | 303 | 147 | 248 | 96.12 |  |  | 327.05 |  | 218.64 | 254.14 | 44.15 |  | 161 | 16 | 95 | [5 empty] | 161 | 16 | 95 | [6 empty] | 161 | 16 | 95 | [8 empty] | 450 | 30 | 70 | 10 | 188 | 185 | 657 |  | m2 | 1 | Painting
12 | Heating pipes + water mains and sewers (of floor above) | 1 | 252.2624 | 29.3071 | 29.7216 | 19.5191 | 20.1021 | 80.7655 | 51.6129 | 174.4287 | 71.8204 | 113.9724 | 70.6333 | 110.1816 | 153.2939 | 0 | 115.7911 | 68.4059 | 96.3693 | 71.8336 | 149.3183 | 63.3992 | 87.2169 | 4.5884 | 108.71 | 107.6339 | 107.6339 | 50.3735 | 146.9617 | 30.8987 | 53.8463 | 27.2834 | 4.0321 | 116.1927 | 94.1389 | 113.7635 | 34.9761 | 119.3488 | 34.3742 | 40.3602 | 58.8813 | 94.0125 | 85.2407 | 55.7059 | 110.3192 | 48.1568 | 53.9712 |  |  |  | 277.6745 | 81.7699 | mh | 1 | Plumbing
13 | Plumbing branches and radiators | 1 | 252.2624 | 29.3071 | 29.7216 | 19.5191 | 20.1021 | 80.7655 | 51.6129 | 174.4287 | 71.8204 | 113.9724 | 70.6333 | 110.1816 | 153.2939 | 0 | 115.7911 | 68.4059 | 96.3693 | 71.8336 | 149.3183 | 63.3992 | 87.2169 | 4.5884 | 108.71 | 107.6339 | 107.6339 | 50.3735 | 146.9617 | 30.8987 | 53.8463 | 27.2834 | 4.0321 | 116.1927 | 94.1389 | 113.7635 | 34.9761 | 119.3488 | 34.3742 | 40.3602 | 58.8813 | 94.0125 | 85.2407 | 55.7059 | 110.3192 | 48.1568 | 53.9712 |  |  |  | 277.6745 | 81.7699 | mh | 1 | Plumbing
14 | Plumbing insulation | 1 | 50.4525 | 5.8614 | 5.9443 | 3.9038 | 4.0204 | 16.1531 | 10.3226 | 34.8857 | 14.3641 | 22.7945 | 14.1267 | 22.0363 | 30.6588 | 0 | 23.1582 | 13.6812 | 19.2739 | 14.3667 | 29.8637 | 12.6798 | 17.4434 | 0.91768 | 21.742 | 21.5268 | 21.5268 | 10.0747 | 29.3923 | 6.1797 | 10.7693 | 5.4567 | 0.80641 | 23.2385 | 18.8278 | 22.7527 | 6.9952 | 23.8698 | 6.8748 | 8.072 | 11.7763 | 18.8025 | 17.0481 | 11.1412 | 22.0638 | 9.6314 | 10.7942 | 0 | 0 | 0 | 55.5349 | 16.354 | mh | 1 | Plumbing
15 | Sprinkler distribution | 1 | 190.0966 | 74.5443 | 47.7497 | 47.0728 | 0 | 91.7648 | 116.389 | 223.712 | 98.4543 | 0 | 0 | 0 | 0 | 35.8071 | 94.6442 | 136.316 | 107.2012 | 138.311 | 0 | 0 | 0 | 40.0009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216.125 |  | mh |  | Fire Sprinkler
16 | Fire stops | 0.2 | 46 | 304 | 56 | 146 | 247 | 92 | 0 | 9 | 242 | 10 | 176 | 83 | 56 | 0 | 150 | 0 | 110 | 0 | 26 | 0 | 1 | 0 | 210 | 109 | 136 | 7 | 290 | 0 | 8 | 91 | 0 | 135 | 109 | 133 | 7 | 478 | 0 | 0 | 92 | 32 | 209 | 0 | 448 | 29 | 72 | 17 | 190 | 35 | 0 | 0 | m2 | 1 | Painting
17 | Acoustic blocking | 0.1 | 125 | 63 | 158 | 0 | 0 | 97 | 112 | 63 | 121 | 127 | 58 | 450 | 212 | 78 | 346 | 445 | 493 | 404 | 152 | 255 | 116 | 85 | 131 | 192 | 194 | 56 | 69 | 184 | 100 | 149 | 3 | 163 | 197 | 187 | 64 | 99 | 142 | 141 | 51 | 282 | 164 | 37 | 114 | 151 | 330 | 64 | 231 | 0 | 0 | 44 | m2 |  | Drywall
18 | Tiling walls and floors + hard concrete floor | 0.9 |  |  | 170 | 247 | 12 | 253 | 30 | 319 | 340 | 131 | 75 | 119 | 230 |  | 111 | 95 | 55 | 87 | 254 | 270 | 306 |  | 111 | 95 | 55 | 87 | 120 | 37 | 249 | 163 | 20 | 111 | 95 | 55 | 87 | 827 | 257 | 308 | 175 |  |  |  | 594 | 36 | 248 |  | 135 |  |  | 23 |  | 1 | Tiling
19 | Closing areas + pressurizing | 1 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | mh
20 | Mechanical Rough | 1 | 53.8915 | 49.8243 | 0 | 37.1448 | 0 | 60.1403 | 77.0706 | 144.7213 | 148.6334 | 0 | 92.9326 | 181.4921 | 0 | 38.6292 | 88.0698 | 100.3586 | 83.9564 | 65.1055 | 183.0081 | 274.8413 | 175.854 | 48.861 | 100.2515 | 87.2322 | 117.048 | 53.9832 | 217.2952 | 146.6486 | 103.267 | 204.6837 | 97.2481 | 105.7083 | 97.9361 | 94.54 | 26.6431 | 310.9938 | 187.6803 | 173.7301 | 120.8396 | 126.1429 | 104.0845 | 22.1924 | 298.3679 | 179.5104 | 173.8078 | 0 |  |  | 931.5267 | 216.6169 | mh | 2 | Mechanical
21 | Mechanical trim | 1 | 53.8915 | 49.8243 | 0 | 37.1448 | 0 | 60.1403 | 77.0706 | 144.7213 | 148.6334 | 0 | 92.9326 | 181.4921 | 0 | 38.6292 | 88.0698 | 100.3586 | 83.9564 | 65.1055 | 183.0081 | 274.8413 | 175.854 | 48.861 | 100.2515 | 87.2322 | 117.048 | 53.9832 | 217.2952 | 146.6486 | 103.267 | 204.6837 | 97.2481 | 105.7083 | 97.9361 | 94.54 | 26.6431 | 310.9938 | 187.6803 | 173.7301 | 120.8396 | 126.1429 | 104.0845 | 22.1924 | 298.3679 | 179.5104 | 173.8078 | 0 |  |  | 931.5267 | 216.6169 | mh | 2 | Mechanical
22 | Mechanical insulation | 1 | 10.7783 | 9.9649 | 0 | 7.429 | 0 | 12.0281 | 15.4141 | 28.9443 | 29.7267 | 0 | 18.5865 | 36.2984 | 0 | 7.7258 | 17.614 | 20.0717 | 16.7913 | 13.0211 | 36.6016 | 54.9683 | 35.1708 | 9.7722 | 20.0503 | 17.4464 | 23.4096 | 10.7966 | 43.459 | 29.3297 | 20.6534 | 40.9367 | 19.4496 | 21.1417 | 19.5872 | 18.908 | 5.3286 | 62.1988 | 37.5361 | 34.746 | 24.1679 | 25.2286 | 20.8169 | 4.4385 | 59.6736 | 35.9021 | 34.7616 | 0 | 0 | 0 | 186.3053 | 43.3234 | mh |  | Mechanical
23 | Cable trays | 1 | 67 | 25 | 6 | 35 | 55 | 65 | 55 | 55 | 50 | 45 | 50 | 60 | 75 | 5 | 18 | 52 | 28 | 20 | 6 | 40 | 12 | 0 | 14 | 30 | 25 | 35 | 60 | 50 | 18 | 40 | 4 | 40 | 30 | 30 | 25 | 4 | 0 | 35 | 30 | 60 | 35 | 46 | 86 | 30 | 30 | 0 |  |  |  |  | mh |  | Electrical
24 | Cabling | 1 | 140 | 84 | 64 | 128 | 60 | 80 | 452 | 184 | 244 | 200 | 560 | 352 | 184 | 180 | 328 | 544 | 236 | 640 | 304 | 632 | 168 | 240 | 384 | 360 | 352 | 460 | 384 | 344 | 256 | 244 | 72 | 292 | 356 | 344 | 276 | 372 | 0 | 304 | 188 | 484 | 612 | 240 | 564 | 396 | 296 | 0 |  |  |  |  | mh |  | Electrical
25 | Painting, surface coat | 0.05 | 1743 | 567 | 496 | 328.32 | 565 | 1429.3 | 704 | 967 | 1066 | 616 | 888 | 2044 | 1834 | 286 | 1013 | 891 | 836 | 414 | 1110 | 1536 | 892 | 365 | 1013 | 891 | 836 | 414 | 1006 | 1308 | 800 | 470 | 111 | 1013 | 891 | 836 | 414 | 1193 | 1306 | 788 | 921 | 1207 | 725 | 170 | 491 | 1266 | 1380 | 786 | 787.74 | 950.82 | 898 | 611.28 | m2 |  | Painting
26 | Electrical fit-out | 1 | 70.2 | 45.3 | 34.95 | 79.6 | 21.95 | 47.65 | 295.35 | 201 | 91.85 | 148.2 | 79.05 | 207.8 | 116 | 91.85 | 155 | 259.35 | 115.7 | 309.7 | 196.8 | 397.1 | 97.05 | 117.75 | 187.15 | 176.5 | 172.3 | 227.4 | 256.85 | 225.5 | 165.45 | 157.4 | 48.2 | 162.85 | 174.6 | 165.85 | 137.7 | 256.15 | 0 | 198.25 | 120.85 | 239.35 | 288.2 | 113.6 | 381.9 | 241.25 | 167.9 | 207.7 |  |  |  |  | mh |  | Electrical
27 | Lights | 1 | 30.6 | 34.8 | 16.8 | 18.6 | 39.6 | 37.2 | 46.2 | 100 | 44.4 | 57.6 | 39.6 | 53.4 | 28.2 | 7.2 | 55.8 | 60.6 | 46.2 | 73.8 | 38.4 | 55.2 | 21.6 | 10.2 | 76.2 | 54 | 48 | 52.8 | 36.6 | 53.4 | 21 | 31.2 | 6 | 55.8 | 53.4 | 48.6 | 42.6 | 52.8 | 0 | 33 | 20.4 | 70.2 | 83.4 | 48 | 56.4 | 28.2 | 30 | 26.4 |  |  |  |  | mh |  | Electrical
28 | Above ceiling connections | 1 | 50.4525 | 5.8614 | 5.9443 | 3.9038 | 4.0204 | 16.1531 | 10.3226 | 34.8857 | 14.3641 | 22.7945 | 14.1267 | 22.0363 | 30.6588 | 0 | 23.1582 | 13.6812 | 19.2739 | 14.3667 | 29.8637 | 12.6798 | 17.4434 | 0.91768 | 21.742 | 21.5268 | 21.5268 | 10.0747 | 29.3923 | 6.1797 | 10.7693 | 5.4567 | 0.80641 | 23.2385 | 18.8278 | 22.7527 | 6.9952 | 23.8698 | 6.8748 | 8.072 | 11.7763 | 18.8025 | 17.0481 | 11.1412 | 22.0638 | 9.6314 | 10.7942 | 0 | 0 | 0 | 55.5349 | 16.354 | mh |  | Plumbing
29 | Suspended ceiling frames | 0.2 | 46 | 304 | 56 | 146 | 247 | 92 |  | 9 | 242 | 10 | 176 | 83 | 56 |  | 150 |  | 110 |  | 26 |  | 1 |  | 210 | 109 | 136 | 7 | 290 |  | 8 | 91 |  | 135 | 109 | 133 | 7 | 478 |  |  | 92 | 32 | 209 |  | 448 | 29 | 72 | 17 | 190 | 35 |  |  | m2 |  | Suspended ceilings
30 | Suspended ceiling installations - MEP | 1 | 10.7783 | 9.9649 | 0 | 7.429 | 0 | 12.0281 | 15.4141 | 28.9443 | 29.7267 | 0 | 18.5865 | 36.2984 | 0 | 7.7258 | 17.614 | 20.0717 | 16.7913 | 13.0211 | 36.6016 | 54.9683 | 35.1708 | 9.7722 | 20.0503 | 17.4464 | 23.4096 | 10.7966 | 43.459 | 29.3297 | 20.6534 | 40.9367 | 19.4496 | 21.1417 | 19.5872 | 18.908 | 5.3286 | 62.1988 | 37.5361 | 34.746 | 24.1679 | 25.2286 | 20.8169 | 4.4385 | 59.6736 | 35.9021 | 34.7616 | 0 | 0 | 0 | 186.3053 | 43.3234 | mh |  | Mechanical
31 | Glass walls | 0.4 |  | 7 |  |  |  |  | 29 | 135 |  | 7 | 8 | 243 | 16 |  | 197 | 272 | 185 | 174 | 63 | 144 | 72 | 18 | 202 | 243 | 257 | 175 | 155 | 64 | 97 | 64 | 35 | 231 | 246 | 232 | 92 | 118 | 84 | 65 | 120 | 217 | 103 | 19 | 177 | 97 | 46 | 130 | 140 |  |  | 74 | m | 2 | Drywall
32 | System walls | 0.8 | [14 empty] | 160 | 128 | 48 | [5 empty] | 111 | 65 | 72 | [6 empty] | 148 | 60 | 65 | [5 empty] | 181 | 56 | 7 |  |  |  |  | 139 |  |  |  | m2 | 2 | Drywall
33 | Millwork (Listoitus) | 0.03 | 349 | 249 | 195 | 144 | 179 | 252 | 235 | 369 | 389 | 326 | 284 | 458 | 345 | 48 | 308 | 345 | 321 | 465 | 359 | 357 | 362 | 32 | 244 | 335 | 310 | 382 | 443 | 277 | 178 | 305 | 69 | 327 | 334 | 289 | 344 | 424 | 300 | 143 | 170 | 441 | 237 | 267 | 320 | 246 | 232 | 299 | 602 | 99 | 173 | 343 | m | 1 | Drywall
34 | Accessories | 1 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | mh | 2 | Drywall
The maximum resources for each trade are as follows:
| Subcontractor | Maximum Resources
| Dust binder painting | 2
| Suspended ceilings | 8
| Drywall | 18
| Electrical | 16
| Fire Sprinkler | 14
| Plasterwork | 10
| Tiling | 20
| Mechanical | 20
| Painting | 20
| Plumbing | 24
Sequence of activities
Item
Dust binder painting
Drywall frame and 1st side
Electric channels
Common hanger system
In-Wall electrical
Drywall insulation and 2nd side
Plasterwork 1 (for wet areas)
Acoustic blocking
Plasterwork 2 (Drywall, ceiling)
Painting - first coat
Acoustic insulation
Sprinkler Rough
Heating pipes + water mains and sewers (of floor above)
Plumbing branches
Sprinkler distribution
Tiling walls and floors + hard concrete floor
Closing areas + pressurizing
Mechanical Rough
Plumbing insulation
Mechanical insulation
Cable trays
Cabling
Painting, surface coat
Above ceiling connections
Mechanical trim
Fire stops
Suspended ceiling frames
Suspended ceiling installations - MEP
Electrical fit-out
Lights
Glass Walls
System Walls
Accessories
Millwork (Listoitus)

## Sheet2
Dist binder painting | 1 | Plumbing work | Plumbing |  |  | Dust binder painting
Drywall frame and 1st side | 2 | Dist binder painting | Dust binder painting |  |  | Suspended ceilings
Common hanger system | 3 | Plasterwork 1 (for wet areas) | Plasterwork |  |  | Drywall
In-Wall electrical | 4 | Common hanger system |  |  |  | Electrical
Drywall insulation and 2nd side | 5 | Drywall frame and 1st side | Drywall |  |  | Fire Sprinkler
Plasterwork 1 (for wet areas) |  | Clean space walls | Drywall |  |  | Plasterwork
Acoustic blocking | 6 | In-Wall electrical | Electrical |  |  | Tiling
Plasterwork 2 (Drywall, ceiling) | 7 | Drywall insulation and 2nd side | Drywall |  |  | Mechanical
Acoustic insulation |  | Electric channels (Sähkökouru) | Electrical |  |  | Painting
Sprinkler Rough | 8 | Refridgerators 1st and 5th floors | Plumbing |  |  | Plumbing
Heating pipes + water mains and sewers (of floor above) | 9 | Sprinkler Rough | Fire Sprinkler
Refridgerators 1st and 5th floors | 10 | Plasterwork 2 (Drywall, ceiling) | Plasterwork
Plumbing work |  | Painting - first coat | Painting
Sprinkler distribution | 11 | Acoustic insulation | Painting
Tiling walls and floors + hard concrete floor | 12 | Heating pipes + water mains and sewers (of floor above) | Plumbing
Closing areas + pressurizing |  | Plumbing branches and radiators | Plumbing
Mechanical Rough | 13 | Plumbing insulation | Plumbing
Plumbing insulation | 14 | Sprinkler distribution | Fire Sprinkler
Mechanical insulation | 15 | Fire stops | Painting
Cable trays | 16 | Acoustic blocking | Drywall
Cabling | 17 | Tiling walls and floors + hard concrete floor | Tiling
Painting, surface coat | 18 | Closing areas + pressurizing
Above ceiling connections | 19 | Mechanical Rough | Mechanical
Fire stops |  | Mechanical trim | Mechanical
Suspended ceiling frames | 20 | Mechanical insulation | Mechanical
Suspended ceiling installations - MEP | 21 | Cable trays | Electrical
Radiator installations | 22 | Cabling | Electrical
Electrical fit-out | 23 | Painting, surface coat | Painting
| 24 | Electrical fit-out | Electrical
|  | Lights | Electrical
| 25 | Above ceiling connections | Plumbing | Mechanical | Fire Sprinkler
| 26 | Suspended ceiling frames | Suspended ceilings
| 27 | Suspended ceiling installations - MEP | Plumbing | Mechanical | Fire Sprinkler
|  | Glass walls | Drywall
|  | System walls | Drywall
|  | Millwork (Listoitus) | Drywall
|  | Accessories | Drywall
| 28 | Radiator installations | Plumbing
0T1
0T2
0T3
0T4
0T5
0T6
1T1
1T2
1T3
1T4
1L1
1L2
1L4
1L5
2T1
2T2
2T3
2T4
2L1
2L2
2L4
2L5
3T1
3T2
3T3
3T4
3L1
3L2
3L3
3L4
3L5
4T1
4T2
4T3
4T4
4L1
4L2
4L3
4L4
5T2
5T3
5T4
5L1
5L2
5L3
5L4
6T2
6T3
6L1
6L2